## Sheet1
Risk ID | Risk Description | Category | Probability | Impact | Mitigation Plan | Owner | Status
R-001 | Material delays | Supply Chain | Medium | High | Secure backup suppliers, expedite orders | John Doe | Ongoing
R-002 | Weather disruptions | Environmental | High | Medium | Contingency schedule, weather monitoring system | Jane Smith | Mitigated
R-003 | Permitting issues | Regulatory | Low | Medium | Proactive communication with authorities | Mark Johnson | New
R-004 | Labor shortage | Human Resources | Medium | Low | Cross-training, recruitment efforts | Sarah Brown | Planned